## Summary
Field | Value
Project | CleverSolutions — Product Gallery / Representative Website
Client / Brand | CleverSolutions (Bulgaria, bg-BG)
Repository | https://github.com/NRGoranov/cleverSolution
Work date(s) | 2026-08-09 — 2026-09-19 (site build, catalogue, brand, UX, remaining publishes)
Role | Full-stack web development (Next.js / React / TypeScript)
Nature of work | Greenfield rebuild of product gallery site (not e-commerce checkout)
Primary CTA | Phone + email (contact form on page, send disabled until reliable)
Stack delivered | Next.js 16.3, React 19.2, TypeScript, Tailwind CSS, Zod, Motion, Playwright, Resend, Vercel-ready
Agreed project envelope | 50 h total (do not exceed)
Total billable hours (mapped) | 50
Day 1 — 09.08.2026 | 6.5 h — project setup, content system, data layer, design tokens
Day 2 — 10.08.2026 | 7.0 h — pages, navigation, contact API, SEO, smoke tests
Day 3 — 11.08.2026 | 6.5 h — upgrade, brand polish, navbar motion, DriftWall backgrounds, handoff
Day 4 — 20.08.2026 | 5.0 h — kitchen catalogue Excel import (39 SKUs + images)
Day 5 — 21.08.2026 | 0.75 h — catalogue text cleanup
Day 6 — 22.08.2026 | 3.5 h — orange brand, logo/favicon, bilingual About page
Day 7 — 23.08.2026 | 3.5 h — hero links, image fit, hours statement, navbar/DriftWall layout
Day 8 — 31.08.2026 | 3.75 h — FAQ/legal pages; portfolio-style mobile menu (overlay, roll-down)
Day 9 — 16.09.2026 | 2.0 h — contact warning + live phone/email; nav stacking above sections
Day 10 — 17.09.2026 | 3.0 h — readable current-page highlights; first 17 wristbands; this statement
Day 11 — 18.09.2026 | 6.5 h — publish kitchen 75 SKUs + remaining 35 wristbands (work ready locally)
Day 12 — 19.09.2026 | 2.0 h — DriftWall photos from new catalogue; final publish QA
Live on GitHub now | 39 kitchen SKUs (live) + 17 vinyl/plastic wristbands; FAQ/legal; contact via phone/email
Publish next few days (already executed locally) | Kitchen → 75 SKUs with new subcategories/photos; wristbands → 52 SKUs (silicone, textile, Tyvek, thermal, RFID)
Outside this 50 h envelope | Real security + cleaning catalogues if/when the client sends files (still demo SKUs)
Currency note | Hours are task-based estimates inside the agreed 50 h project total; adjust rate as agreed

## Hours Log
ID | Date | Phase | Task / Work package | Problem / Challenge | Solution / What was implemented | Hours | Key deliverables / areas
1 | 2026-08-09 | Discovery & setup | Read rebuild brief; scaffold Next.js App Router project with TypeScript, Tailwind, ESLint | Empty workspace; gallery site (not store); production-ready foundation needed | Scaffolded app; path aliases, Tailwind tokens, Cyrillic fonts, base layout, AGENTS conventions | 2 | package.json, app/, tailwind.config.ts, AGENTS.md
2 | 2026-08-09 | Content & i18n | Bulgarian content system for all UI strings | UI must be bg-BG; single editable copy source for non-developer updates | Centralized content/bg.ts for site, nav, hero, categories, product, contact, footer | 1 | content/bg.ts
3 | 2026-08-09 | Data architecture | Zod-validated product data layer for 4 categories; hand-editable placeholders | No CMS; real data from paper records later; schema must stay stable | ProductSchema; per-category files; draft/published; optional price; index helpers | 1.75 | data/products/*
4 | 2026-08-09 | Design system | Tokens, typography, skeletons, SSR-safe motion primitives | Loading states must match layouts; Framer SSR blank-page risk | Ink/canvas tokens; skeleton shimmer; ScrollReveal safe mount pattern | 1.75 | globals.css, components/skeletons, components/motion
5 | 2026-08-10 | Layout & navigation | Header/Footer; category nav; mobile menu; subcategory dropdowns | Four categories; English URL slugs with Bulgarian labels | Sticky header, hover dropdowns, responsive drawer, footer structure | 1.25 | components/layout/Header.tsx, Footer.tsx
6 | 2026-08-10 | Home page | Hero, category grid, featured products, contact CTA block | Brand-first hero with local product photography | Hero10 image fan; HomeSections; primary/secondary CTAs | 1.5 | components/home/*, components/ui/hero-10.tsx, app/page.tsx
7 | 2026-08-10 | Category & product pages | Galleries, coming-soon states, product detail with gallery/specs/JSON-LD | SEO without checkout; async App Router params on Next 16 | CategoryPageContent; ProductGallery/Specs; generateStaticParams; contact deep-link | 1.75 | app/{kitchen,security,wristbands,vacuums}, app/product/[slug]/*
8 | 2026-08-10 | Contact & email | Contact page + Resend API Route Handler | Production email path with env-based configuration | Validated form; POST /api/contact; .env.example | 1.25 | app/contact, components/contact/ContactForm.tsx, app/api/contact
9 | 2026-08-10 | Assets, SEO & QA | Local images, metadata/sitemap, Playwright smoke tests | No remote stock dependency; regression safety before handoff | public/images/*; robots/sitemap; e2e smoke suite (14 paths) | 1.25 | public/images, SEO files, e2e/smoke.spec.ts
10 | 2026-08-11 | Platform upgrade | Upgrade to Next.js 16 and React 19; fix breaking changes | Codemod hung; params Promise migration; build verification | Manual dep upgrade; async params fixes; verified production build | 1.25 | package.json, product page params, eslint-config-next 16
11 | 2026-08-11 | Brand & UX polish | Teal accent, scrollbar, product card Details flow, scroll-to-top, footer credit | Monochrome UI; cards pushed contact too early; mobile polish | brand tokens; ProductCard Details CTA; ScrollToTop; subtle NRG footer link | 1.25 | globals.css, tailwind.config.ts, ProductCard, ScrollToTop, Footer
12 | 2026-08-11 | Navbar motion | Port NRGxPortfolio scroll-shrink navbar behaviour | Client wanted same motion language as portfolio site | Scroll-shrink pill header, cursor sheen, underline hovers, animated mobile menu | 1 | components/layout/Header.tsx
13 | 2026-08-11 | Homepage backgrounds | DriftWall full-page backdrop; layered category/contact panels; inner-page teal gradient | Hero atmosphere vs readable content sections; footer above fixed background | DriftWall + HomePageBackground; MainBackground route switch; PageGradientBackground | 1.75 | DriftWall.jsx, HomePageBackground, PageGradientBackground, HomeSections
14 | 2026-08-11 | Bugfixes & DX | React 19 script warning, Windows .next cache, JSON-LD, dev scripts | Balancer script tag; dev server lock; console warnings | Removed react-wrap-balancer; clean/dev:fresh; data-scroll-behavior; JSON-LD pattern | 0.75 | hero-10.tsx, package.json scripts, app/layout.tsx
15 | 2026-08-11 | Client handoff prep | Product Excel import template; hours statement; git push to GitHub | Client needs format for 150–180 products; billing documentation | CleverSolutions-Produktov-shablon.xlsx; work-hours statement; commits on main | 0.5 | docs/*, scripts/generate-product-template.py, GitHub main branch
16 | 2026-08-20 | Catalogue import | Import kitchen equipment Excel into published products with images | 150–180 SKU catalogue; first real data was a multi-sheet Excel with embedded photos | import-catalogue.py: sheet→subcategory map, image extract, slugify, Zod-ready kitchenware.ts | 5 | scripts/import-catalogue.py, data/products/kitchenware.ts, public/images/products/*
17 | 2026-08-21 | Catalogue QA | Normalize imported catalogue text endings and incomplete punctuation | Excel cells had truncated sentences and inconsistent spacing | Cleaned descriptions/specs in kitchenware.ts without changing product count | 0.75 | data/products/kitchenware.ts
18 | 2026-08-22 | Brand & About | Orange/black palette, logo mark favicon, bilingual За нас page | Client asked for About copy, warmer color, logo colors black+orange | Brand tokens #FF6000; BrandLogo; /about BG+EN; nav/footer; icon/apple-icon/favicon | 3.5 | content/bg.ts, app/about, BrandLogo, globals.css, app/icon.png
19 | 2026-08-23 | Homepage & product photos | Hero fan links to categories; 7-column DriftWall; contain product images | Carousel photos needed to be category buttons; SKU photos cropped out of frames | Clickable hero slides; column-grouped DriftWall; object-contain on cards/gallery | 1.75 | Hero.tsx, hero-10.tsx, hero-drift-images.ts, ProductCard, ProductGallery
20 | 2026-08-23 | Billing estimate | Update work-hours statement and remaining 150–180 SKU ballpark | Client needs hours-to-date plus time to finish remaining products | Extended hours log to 31.5 h; Remaining SKUs sheet with scenario ranges | 0.5 | scripts/generate-work-statement.py, docs/CleverSolutions-Work-Hours-Statement-client.*
21 | 2026-08-23 | Layout polish — published | Fill DriftWall on wide screens; full-width then compact scrolled navbar | Backdrop columns stopped at 7 on large monitors; navbar did not span the viewport | Filled DriftWall to viewport; 100vw top bar; compact centered pill on scroll; type tweaks | 1.25 | Header.tsx, DriftWall, globals.css; commits 28b89d4, d5afbe9, a680154
22 | 2026-08-31 | Legal & FAQ — published | FAQ and legal pages; portfolio-style mobile navbar | No FAQ/privacy/terms; burger menu needed to match NRGxPortfolio behaviour | Added /faq /privacy /terms; FAQ JSON-LD; mobile menu copied from portfolio pattern | 2.25 | app/faq, app/privacy, app/terms, FaqPreview, Header.tsx; commit 398477d
23 | 2026-08-31 | Mobile nav — published | Menu must float over the page, roll down, no burger border | Open menu expanded/stuck the header and pushed the whole layout | Portal overlay; height animation from the bar; borderless burger; page no longer shifts | 1.5 | Header.tsx; commits 5c9dad8, fdb698f
24 | 2026-09-16 | Contact & FAQ — published | Disable unreliable send; live phone/email; clickable FAQ answers | Form did not send smoothly; old placeholder contacts; FAQ had no links | Warning + disabled submit; +359 888 250 818 and office@cleversolution.bg; markdown FAQ links | 1.5 | ContactForm.tsx, content/bg.ts, FaqAnswer.tsx, lib/faq.ts; commit 0b532af
25 | 2026-09-16 | Navbar stacking — published | Desktop bar and category dropdowns above page sections | Menus painted under hero/category cards (overflow + z-index) | Raised header stacking; overflow visible; dropdowns sit on top of content | 0.5 | Header.tsx, app/layout.tsx; commit bf7a3af
26 | 2026-09-17 | UX + catalogue — published | Readable current-page highlights; first third of wristband catalogue | Active labels matched the peach background; wristbands still demo SKUs | Darker/slightly scaled current item; 5px chip padding; 17 vinyl + Superband/SureImage SKUs live | 2.5 | Header, CategorySubnav, data/products/wristbands.ts, public/images/products/wristbands/*; commit aa2e01f
27 | 2026-09-18 | Kitchen catalogue — publish next days | Expand kitchen from 39 to 75 SKUs with new subcategories and photos | Client sent a fuller Equipment Excel (all sheets, WAVE 1, fridge tables, ranges) | Executed locally: importer + 75 published products, 8 kitchen subs; commit to main in the next days | 3.5 | scripts/import-catalogue.py, data/products/kitchenware.ts, content/bg.ts, public/images/products/*
28 | 2026-09-18 | Wristbands catalogue — publish next days | Remaining two-thirds of wristbands (35 SKUs) | 17 of 52 live; silicone, textile, Tyvek, thermal, RFID, holographic plastic still local | Executed locally from scheme.xlsx + Word docs; publish remaining families in the next days | 3 | data/products/wristbands.ts, import-wristbands.py, public/images/products/wristbands/*
29 | 2026-09-17 | Billing — this statement | Map remaining work into the agreed 50 h envelope | Previous log stopped at 31.5 h and still quoted 24–36 h extra for 150–180 SKUs | Extended log through 19.09; remaining publishes sit inside 50 h; no overshoot | 0.5 | scripts/generate-work-statement.py, docs/CleverSolutions-Work-Hours-Statement-client.*
30 | 2026-09-19 | Wrap-up — scheduled | Homepage DriftWall photos from new SKUs; publish QA; close 50 h envelope | New kitchen/wristband photos not yet on the live backdrop; remaining git publish | Swap DriftWall tiles to new catalogue shots; verify category/product routes after push | 2 | lib/hero-drift-images.ts, GitHub main, Playwright smoke

## Problems Solutions
ID | Problem | Impact | Resolution | Status
P1 | Empty repo / greenfield rebuild from detailed brief | No existing code to extend | Full scaffold + feature build against placeholder Zod dataset | Resolved
P2 | Product data not ready; must be hand-editable later | Risk of CMS/admin overbuild | File-based Zod data; drafts hidden; Bulgarian editor comments in data files | Resolved
P3 | Windows .next cache lock / corrupted build artifacts | Dev server hung; blocked iteration | clean + dev:fresh scripts; delete .next/cache when locked | Resolved
P4 | Blank page from Framer Motion SSR opacity:0 | Homepage appeared empty | ScrollReveal SSR-safe: plain div until mounted | Resolved
P5 | Cyrillic vs Latin URL/slug confusion | Unstable routing/SEO | English route slugs; Bulgarian UI copy only | Resolved
P6 | Next.js interactive upgrade codemod hung | Blocked framework upgrade | Manual Next 16 / React 19 dependency upgrade + API fixes | Resolved
P7 | Next.js warning: missing data-scroll-behavior with smooth scroll | Console noise; route transition scroll UX | Added data-scroll-behavior="smooth" on <html> | Resolved
P8 | React 19: Encountered a script tag from react-wrap-balancer | Console error on homepage hero | Removed library; native CSS text-wrap: balance | Resolved
P9 | Product card conversion path unclear | Contact CTA too early in browse flow | Details button to product page; contact on detail only | Resolved
P10 | DriftWall background readability on homepage | Featured heading hard to read over dark tiles | Frosted panel on featured header; layered section backgrounds | Resolved
P11 | Inner-page teal gradient too strong then invisible | Background tuning iterations | Top-down softer wash; later replaced with warm orange from logo | Resolved
P12 | Product photos overflowed frames / not centered | Catalogue images cropped on cards and detail gallery | object-contain + padding on ProductCard and ProductGallery | Resolved
P13 | Missing За нас and teal palette vs logo | No About page; brand colors did not match black/orange logo | Bilingual /about; #FF6000 tokens; logo + C-mark favicon | Resolved
P14 | Remaining 150–180 SKUs not yet on the site | Original estimate assumed a much larger mixed catalogue | Client files covered kitchen (75) + wristbands (52). Those fit inside the 50 h cap; security/vacuums stay demo until new files arrive | Kitchen + wristbands mapped in this envelope; other categories waiting on client
P15 | Mobile burger menu stuck the navbar and pushed the page | Layout jumped; overlay felt like a full-page takeover | Portal menu floats over content; rolls down from the bar; no burger border | Resolved
P16 | Contact form send was not reliable | Enquiries could be lost if users trusted the submit button | Visible warning; send disabled; phone +359 888 250 818 and office@cleversolution.bg | Resolved (form stays off until delivery is stable)
P17 | Desktop nav and dropdowns sat behind page sections | Category menus unusable over hero/cards | Higher header z-index; overflow visible so menus paint on top | Resolved
P18 | Current-page highlight matched the peach page wash | КАТЕГОРИИ / active chips hard to read; first chip clipped after scale | Darker current-page color; slight scale; 5px left padding on first chip | Resolved

## Deliverables
Area | Items delivered
Public routes | / · /about · /faq · /privacy · /terms · /kitchen · /security · /wristbands · /vacuums · /product/[slug] · /contact
API | POST /api/contact (present; send button disabled until reliable)
Data model | Zod Product schema; 39 kitchen SKUs live (75 ready to publish); 17 wristbands live (52 ready to publish); security/vacuums still samples
UI surfaces | Hero, FAQ accordion with links, legal pages, category grids, product cards/detail, contact warning + phone/email, coming soon, skeletons
SEO | Metadata, Open Graph, JSON-LD Product + FAQ, sitemap/robots
Tests | Playwright smoke + site-health (contact disabled-form checks)
Ops | Vercel-oriented Next 16 app; env example; clean/dev:fresh scripts
Git milestones | 910e54c initial · 4c816f6 kitchen 39 · e0cd666 brand/About · 398477d FAQ/mobile nav · 0b532af contact/phone · aa2e01f 17 wristbands

## Mapped remaining
Work package | SKU / scope | Execution | Hours (inside 50 h) | Status | Notes
Kitchen expansion | +36 SKUs (39 → 75) + new subcategories/photos | Already built locally — commit 18.09 | 3.5 | Scheduled publish | Hours in log ID 27
Wristbands remainder | +35 SKUs (17 → 52) | Already built locally — commit 18.09 | 3 | Scheduled publish | Hours in log ID 28
DriftWall + publish QA | New photos on homepage; verify routes after push | Scheduled 19.09 | 2 | Scheduled wrap-up | Hours in log ID 30
This hours statement | Map work to 50 h cap | Executed 17.09 | 0.5 | Done | Hours in log ID 29
Security + cleaning real catalogue | Still 8 demo SKUs | Waiting on client Excel/photos | 0 | Out of envelope | Not billed inside 50 h unless new files arrive
Contact form send | Button stays disabled | Re-enable only when delivery is stable | 0 | Parked | Use wrap-up buffer only if requested inside 50 h