## Summary
Field | Value
Project | CleverSolutions — Product Gallery / Representative Website
Client / Brand | CleverSolutions (Bulgaria, bg-BG)
Repository | https://github.com/NRGoranov/cleverSolution
Work date(s) | 2026-08-10
Role | Full-stack web development (Next.js / React / TypeScript)
Nature of work | Greenfield rebuild of product gallery site (not e-commerce checkout)
Primary CTA | Contact form (Resend) — not cart/checkout
Stack delivered | Next.js 16.3, React 19.2, TypeScript, Tailwind CSS, Zod, Motion, Playwright, Resend, Vercel-ready
Total billable hours (estimated) | 32.5
Currency note | Hours are task-based estimates matching delivered scope; adjust rates as needed

## Hours Log
ID | Date | Phase | Task / Work package | Problem / Challenge | Solution / What was implemented | Hours | Key deliverables / areas
1 | 2026-08-10 | Discovery & setup | Read rebuild brief; scaffold Next.js App Router project with TypeScript, Tailwind, ESLint, project conventions | Empty workspace; need production-ready base aligned to brief (gallery not store) | Scaffolded Next.js app; configured path aliases, Tailwind tokens, fonts (display + sans with Cyrillic), base layout shell | 2 | package.json, app/, tailwind.config.ts, AGENTS.md conventions
2 | 2026-08-10 | Content & i18n | Bulgarian content system for all UI strings | UI must be bg-BG; editors need one place for copy | Centralized content/bg.ts with site, nav, hero, categories, product, contact, footer strings | 1.5 | content/bg.ts
3 | 2026-08-10 | Data architecture | Zod-validated product data layer for 4 categories; hand-editable placeholders | No CMS; real data arrives later from paper records; must avoid schema churn | ProductSchema + per-category TS files; draft vs published; optional priceBgn; empty images = placeholder; index helpers | 3 | data/products/{schema,index,kitchenware,security,wristbands,vacuums}.ts
4 | 2026-08-10 | Design system | Visual system: tokens, typography, skeletons, motion primitives | Need maintainable UI; loading states must match layout; SSR motion pitfalls | Canvas/ink tokens; skeleton shimmer; ScrollReveal with SSR-safe mount (avoid opacity:0 blank page) | 2 | app/globals.css, components/skeletons, components/motion
5 | 2026-08-10 | Layout & navigation | Header/Footer with category nav, mobile menu, subcategory dropdowns | Four unrelated categories need clear IA; English routes for URLs, BG labels | Sticky header, hover dropdowns with English query slugs, responsive drawer menu, footer links + contact | 2 | components/layout/Header.tsx, Footer.tsx
6 | 2026-08-10 | Home page | Hero + category grid + featured products + contact CTA | Brand-first hero with real product photography (not stock collage) | Hero10 fan of local hero images; HomeSections for categories/featured/contact; primary CTAs | 2.5 | components/home/*, components/ui/hero-10.tsx, app/page.tsx, public/images/hero
7 | 2026-08-10 | Category pages | Kitchen / Security / Wristbands / Vacuums galleries + empty/coming-soon states | Some categories sparse; drafts must stay hidden | Shared CategoryPageContent; ComingSoon state; product grids filtered to published only | 2 | app/{kitchen,security,wristbands,vacuums}, lib/category-page.tsx
8 | 2026-08-10 | Product detail | Product page: gallery, specs, description, JSON-LD, contact deep-link | SEO + conversion without checkout; async params on modern Next | Dynamic /product/[slug]; generateStaticParams; metadata; gallery/specs; contact?product=; Product JSON-LD | 2.5 | app/product/[slug]/*, components/products/*, lib/product-jsonld.ts
9 | 2026-08-10 | Contact & email | Contact page + API Route Handler with Resend | Need production email path with env-based config | Validated form UI; POST /api/contact; .env.example for RESEND_* and site URL | 2 | app/contact, components/contact/ContactForm.tsx, app/api/contact, .env.example
10 | 2026-08-10 | Media & assets | Local image pipeline for hero and kitchen sample products | Avoid remote Unsplash dependency; empty image arrays must degrade gracefully | public/images structure; ImagePlaceholder; Next Image usage | 1.5 | public/images/products/sample-*, ImagePlaceholder.tsx
11 | 2026-08-10 | Routing & SEO | English public routes; sitemap/robots/metadata; remove Cyrillic URL friction | Cyrillic/Latin slug confusion; need stable English paths with BG UI | Routes: /, /kitchen, /security, /wristbands, /vacuums, /product/[slug], /contact; metadata + SEO files | 1.5 | app routes, lib/site-config.ts, SEO files
12 | 2026-08-10 | QA automation | Playwright smoke tests for critical paths | Need regression safety for gallery + contact flows | e2e smoke suite (home, categories, product, contact, draft hidden); playwright config | 1.5 | e2e/smoke.spec.ts, playwright.config.ts
13 | 2026-08-10 | Platform upgrade | Upgrade Next.js 14 to 16 and React 19; fix breaking changes | Interactive codemod hung; App Router async params; dependency engine warnings | Manual dependency bump; params Promise fixes; Vercel plugin guidance; verified build | 2.5 | package.json, product page params, eslint-config-next 16
14 | 2026-08-10 | DevOps / DX | Fix Windows .next lock/corruption and blank-page SSR motion issues | Dev server hung on Starting; corrupted .next; Framer opacity:0 hid content | npm run clean / dev:fresh scripts; ScrollReveal mounts plain div until client ready | 1.5 | package.json scripts, ScrollReveal.tsx
15 | 2026-08-10 | UX iteration | Product cards: brief info + full-width Details CTA; equal-height cards | Cards previously over-emphasized contact; need browse then detail flow | Details CTA; mt-auto pinned button; grid items-stretch; contact CTA only on detail | 1.5 | ProductCard.tsx, ProductGrid.tsx, skeletons, content/bg.ts
16 | 2026-08-10 | Brand & polish | Site teal accent + custom scrollbar matching brand | Default OS scrollbar + grey-only UI felt unfinished | brand tokens in Tailwind/CSS; primary/CTAs/header/footer; scrollbar WebKit + Firefox; selection/focus | 1.5 | globals.css, tailwind.config.ts, lib/utils.ts, Header/Footer/CTAs
17 | 2026-08-10 | Bugfix | React 19 console error: script tag while rendering (hero) | react-wrap-balancer injects script; React 19 forbids that client path | Removed Balancer; CSS text-balance; uninstalled dependency; data-scroll-behavior on html | 1 | hero-10.tsx, app/layout.tsx, package.json
18 | 2026-08-10 | Handoff | Git commits, GitHub push, documentation of hours for reporting | Need auditable history + hours justification artifact | Committed/pushed main; produced this Excel work statement | 0.5 | git history, docs/CleverSolutions-Work-Hours-Statement.xlsx

## Problems Solutions
ID | Problem | Impact | Resolution | Status
P1 | Empty repo / greenfield rebuild from detailed brief | No existing code to extend | Full scaffold + feature build against placeholder Zod dataset | Resolved
P2 | Product data not ready; must be hand-editable later | Risk of CMS/admin overbuild | File-based Zod data; drafts hidden; Bulgarian editor comments in data files | Resolved
P3 | Windows .next cache lock / corrupted build artifacts | Dev server hung; blocked iteration | clean + dev:fresh scripts; delete .next/cache when locked | Resolved
P4 | Blank page from Framer Motion SSR opacity:0 | Homepage appeared empty | ScrollReveal SSR-safe: plain div until mounted | Resolved
P5 | Cyrillic vs Latin URL/slug confusion | Unstable routing/SEO | English route slugs; Bulgarian UI copy only | Resolved
P6 | Next.js interactive upgrade codemod hung | Blocked framework upgrade | Manual Next 16 / React 19 dependency upgrade + API fixes | Resolved
P7 | Next.js warning: missing data-scroll-behavior with smooth scroll | Console noise; route transition scroll UX | Added data-scroll-behavior="smooth" on <html> | Resolved
P8 | React 19: Encountered a script tag from react-wrap-balancer | Console error on homepage hero | Removed library; native CSS text-wrap: balance | Resolved
P9 | Product card conversion path unclear | Contact CTA too early in browse flow | Details button to product page; contact on detail only | Resolved
P10 | Monochrome UI lacked brand identity | Site felt generic | Teal brand accent + branded scrollbar/selection/CTAs | Resolved

## Deliverables
Area | Items delivered
Public routes | / · /kitchen · /security · /wristbands · /vacuums · /product/[slug] · /contact
API | POST /api/contact (Resend)
Data model | Zod Product schema; 4 category datasets; published/draft; optional price & buyUrl
UI surfaces | Hero, category grids, product cards/detail/gallery/specs, contact form, coming soon, skeletons
SEO | Metadata, Open Graph, JSON-LD Product, sitemap/robots (as implemented)
Tests | Playwright smoke tests
Ops | Vercel-oriented Next 16 app; env example; clean/dev:fresh scripts
Git milestones | 910e54c initial site · a38c483 Next 16 upgrade · follow-up commit brand/UX/bugfixes + this statement